Timeline for planning and implementing your CPR Training Events

1-2 months before event

- Designate a primary leader for your event. Allocate other roles to other members of the group. Meet to assign other duties on this timeline for planning/implementation.

- Contact school administration about event. Register event.

- Plan out scope of event (estimate number of participants, number of trainings over what time period) and budget required for event.

- Contact chapter head about event/discuss funding and partnering with other chapters to split funding.

1 month before event

- Order CPR in Schools Training Kit(s)™ from American Heart Association (Click Buy Now at heart.org/cprinschools)

- Reserve location on campus to hold training event. Fill out appropriate paperwork for school related to reserving the building and a TV/Projection System/DVD player.

- Schedule email blast to all students if possible.

3 weeks before event

- Print flyers and posters.

- If school requires approval of promotional materials, get approval prior to printing.

2-3 weeks before event (or as appropriate for your school)

- Put up flyers and posters in areas around campus (if applicable).

- Order food (timing of ordering depends on university).

- Send out first email blast to whole student body (if applicable).

- Contact presidents of other Greek Organizations on campus and speak at their chapter meetings to invite them to participate in the event.

- Create Facebook/social media event.

- Encourage all members of the sponsoring organization to invite students (and staff) to the event.

1-2 weeks before event

- Send out two email reminders to students to encourage registration.

- Update Facebook event and post reminders on all social media sites to increase excitement.

- Post videos from the AHA CPR in Schools website about CPR (See www.heart.org/cprinschools)

1 week before event

- Have the students leading the training familiarize themselves with the CPR in Schools Training Kit™ (watch DVD and review lesson plan) and watch the webinar available once kits are purchased.

Day before the event

- Send email reminder to students who have registered.

Day of event

- Bring CPR training kit, prizes, giveaways, and incentives to location.

- Pick up food.

- Set up manikins and handouts before event starts.

- Test TV/Projection System/DVD player.

- Facilitate training.